## Slide 1
Indian Creek Drive Flooding Mitigation Project Phase 3
Wednesday, November 13, 2019
Notes: Heather will welcome the group and introduce elected officials.

## Slide 2
Presented by:
Maher Maaliki, P.E. Consultant Project Manager Ribbeck Engineering, Inc.
Mauricio Arze, P.E. Senior Project Engineer WSP USA Inc.
Mina Samadi, P.E. City of Miami Beach Senior Capital Projects Coordinator Office of Capital Improvement Projects
Michael Fischer RIC-MAN Construction Florida, Inc. Chief Operating Officer Contractor
Notes: Heather will introduce team members

## Slide 3: Presentation Outline
1
2
Questions/Comments
3
What to Expect During Construction
5
Where We Are Now
Why is this Project Needed/Overview
4
Project Phasing
Notes: HL will describe format and hand off to Mina

## Slide 4: Where We Are Now
1
Notes: Mina

## Slide 5: Where We Are Now
Ongoing Activities
Contractor issued Notice to Proceed (NTP)
  Reviewing corridor and existing field conditions
  Setting up field trailer and bringing equipment to site
  Performing preliminary survey work
  Verifying location and elevation of utilities (this may require lane closures if a utility is in a travel lane)
  Cleaning areas near pump station at 32 Street
  Working with city and agencies to obtain all necessary permits
  Preparing construction work plans and drawings
Continue to meet with property representatives to review project impacts and execute License Agreements
  Reach out to your property manager or HOA board for more information
  Deadline to submit executed agreement: November 30, 2019
Notes: Mina

## Slide 6: Executed License Agreements
Notes: Mike
Highlight the numbers of properties and the ones who haven’t submitted.

## Slide 7: Project Overview
Improvements
Continuing stormwater drainage improvements on Indian Creek Drive and side streets, including completing the stormwater pump station at 32 Street
Final restoration of the roadway and sidewalk on Collins Avenue between 25 Street and 26 Street
Rebuilding and raising the roadway with ADA-compliant sidewalks on Indian Creek Drive between 26 Street and 41Street
Installing new signage and pavement markings
Installing new street lighting
Installing new traffic signals at 26, 29 and 39 streets
Harmonization: connecting the new roadway elevation to existing properties
Access to properties will be maintained unless coordinated in advance.
As the work progresses, sections of on-street parking will be temporarily unavailable.
Notes: Mina

## Slide 8: Why is this Project Needed/Overview
2
Notes: Mina

## Slide 9: Project Need/Overview
Pre-Construction Conditions: 2015
Indian Creek Drive
at 32 Street
Notes: Mina
Move under caption

## Slide 10: Project Need/Overview
Pre-Construction Conditions: May 2018
Notes: Mina

## Slide 11: Project Need/Overview
Pre-Construction Conditions: November 2019
Notes: Mina

## Slide 12: Project Overview
Limits
Preliminary work started October 11
Full construction will not begin until all permits are obtained
Anticipated project duration once full construction starts: 19 months
Indian Creek Drive between 26 Street and 41 Street
Collins Avenue between 25 Street and 26 Street
Project Schedule
Notes: Mina

## Slide 13: Typical Infrastructure Layout
Notes: Mina

## Slide 14: Typical Infrastructure Layout
Notes: Mina

## Slide 15: Project Phasing
3
Notes: Mina handoff to Mike

## Slide 16: Project Phasing
How Does it Work?
Divided into two main phases
Each phase is divided into smaller sections
  10 work zones, approximately 500 feet long
Contractor works in one section at a time to complete as much work as possible before moving onto next section
All underground utility work, drainage, sidewalks, road reconstruction, first layer of asphalt, signage, signals, lighting and harmonizations will be complete
Final layer of asphalt and pavement markings will be placed all at once toward the end of the project to ensure uniformity and consistent appearance
Notes: Mike

## Slide 17: Project Phasing
Notes: Mike

## Slide 18: Project Phasing
Anticipated project timeline
Phase I
  Beginning in Section 6 working to Section 10
  From 31 Street to 41 Street
  Working south to north
  Overall expected timeframe in this area: 11.5 months
Phase II
  Work in Section 1 to Section 5
  From 25 Street to 31 Street
  Working south to north
  Overall expected timeframe in this area: 7.5 months
  Please note this schedule may change due to weather or other unforeseen conditions.
Notes: Mike

## Slide 19: Phase I: Sector’s 6 through 8
Notes: Mike

## Slide 20: Phase I: Sector’s 9 and 10
Notes: Mike

## Slide 21: Phase II: Sector’s 1 through 4
Notes: Mike

## Slide 22: Phase II: Sector’s 4 and 5
Notes: Mike

## Slide 23: Project Phasing
Benefits
Fully dedicates resources to one section at a time
Shortens the overall duration of work in a given area
  Average duration in each section is approximately eight weeks
Community will see progress within each section rather than experiencing work in multiple phases
  Including harmonization
Minimizes construction traffic impacts along Indian Creek Drive as the entire road will not be an open work zone
Local traffic will be maintained within active sections
  General traffic will be detoured around the work
  Final Maintenance of Traffic (MOT) pending City and FDOT approval
Notes: Mike

## Slide 24: What to Expect During Construction
4
Notes: Mike

## Slide 25: What to Expect…
Notes: Mike

## Slide 26: What to Expect…
Notes: Mike

## Slide 27: What to Expect…
Notes: Mike

## Slide 28: Questions/Comments
5
Notes: Lynn will facilitate Q&A

## Slide 29: For more information please contact: Heather M. Leslie, Public Information Liaison 305.905.5876 Heather@hmlpublicoutreach.com
Notes: Heather will thank everyone for attending